## Risk Register
Risk Register : Joint Camp 2021 Version Number 0.1 Date: 19/11/2021 - 22/11/2021 Contributors: JA, JS, EA
ID | Generic Risk | Specific Risk | Consequence of the specific risk | What could cause this (causal Factors) | Likelihood Rating | Consequence Rating | Risk Rating | Risk owner (person organising event) | Controls (think of event from Marketing through to event end) | Residual Risk (risk rating following the implementation of controls) | Actions/Comments | Action Owner | Critical Dates / Ongoing | Priority of Action. 1 to 5 with 1 being the most important
1 | Health and Safety | Death or Injury from Intoxication | Falling over causing minor or serious injury, bad behaviour, brain and spinal injuries death. | A: Intoxication causing loss of balance/poor decision making/aggression | Possible | Major | Extreme | JS / JA / EA | a; Code of Conduct to clearily indicate expected behaviours and RSA processes will be followed, no one showing signed of intoxication or under the influence of drugs will be permitted access to the camp. b; Management of alcohol, RSA legislation will be strictly adhered to. Water will be freely available from numerous locations. Food will be available through the duration of the camp c; First Aid - Qualified first aid officers designated throughout the event. FAO must be 0% BAC d; Signage - Ensuring signage is visable stating that water is available FOC from multiple locations and that RSA practices will be followed | Major | i: Effective Marketing and Code of Conduct ii: Thorough staff briefing signed by all staff iii: Check for current first aid certificates iv: Obtain all RSA certs v: Produce all signage where water is vi: Erect all signage on the camp | i JS ii JS iii JA iv EA v JA vi EA | I ongoing ii 19/11 iii 19/11 iv 19/11 v 19/11 vi 19/11 | I 4 ii 1 iii 2 iv 3 v 5 vi 6
2 | Legislative Requirements (Duty of Care) | Uninvited Persons try to attend, guests are refused entry due to showing signs of intoxication and try to re-enter. | Financial Loss Potential risk to guest onboard Reputation | A: Someone has lost their ticket and cannot gain entry B: Patrons advised that they are not permitted entry to the event C: People see the event and want to attend | Unlikely | Insignificant | Low | JS / JA / EA | i: Marketing - Clearly indicate it is a ticket/invite only event. Marketing to clearly state 18+ event. ID required. Drink Responsibly ii: Guest list will be used to identify rightful attendees iii: ID will be checked upon ticket purchase iv: Tickets will only be sold to club members to decrease chance of unruly strangers attending v: Manjedal Activity manager will be called if univited individual try to enter and they can choose to notify police | Low | i: Effective marketing ii: Guest list will be used to identify attendees arriving at camp. Only those who have been previously and specifically invited to do so will be able to purchase tickets at the door. iii: Check ID's on ticket sales, including for those purchasing tickets at camp. iv: Check club membership on ticket sales. v: Have Manjedal contact available to all camp leaders and committee members. | i: JS ii: JS iii: JS iv: EA v: EA | i: ongoing ii: 19/11 iii: ongoing iv: ongoing v: 19/11 | i: 3 ii: 2 iii: 1 iv: 5 v: 4
3 | Health and Safety | Sexual Harrasment/Sexual Assault | Vulnerable, Abuse, affect reputation of student and UWA | A: Predatorial behaviour B: Intoxication causing reduction in inhibitions and poor decision making C: Intoxication leading to inability to consent D: Sexually charged environment E: dark corners for predators to lurk | Unlikely | Major | Moderate | JS / JA / EA | i: Code of Conduct: Specify appropriate behaviours ii: Single-gender dorms available for both men and women iii: Event staff monitoring behaviours iv: RSA staff and bar manager ensuring that RSA requirements are adhered to v: RSA checkers offerring water to those nearing intoxication vi: Lights will be on during all activities and drinking hours | Minor | i: effective marketing ii: thourough staff briefing iii: water easily available at central location during camp iv: single-gender and mixed dorms will be signed v: ensure legitimate single-sex dorms are maintained | i: JS ii: JS iii: JA iv: EA v: EA | i: ongoing ii: 19/11 iii: 19/11 iv: 19/11 v: ongoing | i: 4 ii: 3 iii: 5 iv: 2 v: 1
4 | Health and Safety | Dehydration | Headaches, increased intoxication, death | A: Not drinking enough water, B: excessive alcohol consumption | Likely | Major | Extreme | JS / JA / EA | i: Water freely available ii: Signage clearly showing water stations iii: Multiple water stations available iv: A range of good non alcoholic beverages v: RSA may refuse providing of alcohol to intoxicated camp attendees | Minor | i: provide water stations ii: provide non-alcoholic drinks free iii: RSA staff rostered at all times | i: JA ii: EA iii: EA | i: 19/11 ii: ongoing iii: 19/11 | i: 1 ii: 2
5 | Health and Safety | Disorderly conduct, aggression, bullying, peer pressure | Potential injury to another guest Emotional distress Arrest Hospitalisation as a result of injury | A: Intoxication causing poor decision making B: Univited Patrons C: Bad behaviour | Possible | Moderate | Moderate | JS / JA / EA | i: RSA procedures followed ii: Only club members allowed to attend so should be aware of general standards of behaviour iii: Event staff briefed to monitor disorderly or suspicious behaviour iv: Qualified first aid officers onsite v: Attendee code of conduct made available to all attendees prior to the camp vi: Attendee agreement signed on ticket purchase | Minor | i: Effective staff briefing ii: Obtain first aid officers certificates and first aid kit. Ensure all first aiders and event staff know location of defib and process to call manjedal manager first if an ambulance is required iii: distribute code of conduct iv: ensure attendee agreement signed v: check attendees are members of at least one of the three attending clubs | i: JS ii: JA iii: EA iv: EA v: EA | i: 19/11 ii: 19/11 iii: 19/11 iv: ongoing v: ongoing | i: 2 ii: 1 iii: 3 iv: 4 v: 5
6 | Reputation | Damage to camp facilities by patrons | Repairs may be required, injury to person commiting crime, negative perception of the club | A: Disorderly behaviour B: Person being denied entry or evicted causing damage C: Accidental damage | Rare | Moderate | Moderate | JS / JA / EA | i: RSA procedures followed ii: evicted patrons will be taken home by sober camp leaders or committee members; Manjedal manager will be called if necessary iii: Manjedal manager can call police if necessary | Minor | i: Effective Staff briefing ii: Camp leaders and committee members monitoring activities | i: JS ii: JS | i: 19/11 ii: ongoing | i: 1 ii: 2
7 | Health and Safety | Fire and Bushfire | Death, Burns | Campfire, smoking, BBQ | Rare | Major | Moderate | JS / JA / EA | i: Fire extinguisher situated next to cooking equipment ii: Smoking not allowed within 10 metres of camp building iii: BBQ only used by camp leaders iv: Campfire monitored by a camp leader at all times while lit v: Campfire put out thouroughly each night vi: Evacuation Plan of Manjedal detailed to camp attendees and followed in the event of an emergency | Minor | i: Effective Staff briefing ii: Fire extinguisher signed iii: Watch campfire iv: Put out campfire v: Brief evacuation plan to camp attendees | i: JS ii: JS iii: EA iv: EA v: JS | i: 19/11 ii: 19/11 iii: ongoing iv: ongoing v: 19/11 | i: 1 ii: 5 iii: 2 iv: 4 v: 3
8 | Health and Safety | Slips, trips and falls | Limb break Grazes, cuts, scratches, scrapes Head injury | A: Cables uncovered B: Wet Floor C: Objects in walk ways | Possible | Minor | Minor | JS / JA / EA | i: Health and Safety :All cables covered ii: Ensure floors are clear of trip hazards before event start iii: Have wet floor signs available for use iv: Have qualified first aiders available | Minor | i: Event staff brief and actions allocated for event day ii: Cabels covered iii: First aiders wearing identifying lanyand | i: JS ii: EA iii: JA | i: 19/11 ii: 19/11 iii: ongoing | i: 1 ii: 2 iii: 3
9 | Health and Safety | Food poisoning | Sickness, | A: BBQ food not being stored properly before event B: BBQ food not being cooked properly C: Bacteria transfer from hands to food | Possible | Moderate | Moderate | JS / JA / EA | i: Food safety training has been completed ii: Food stored correctly iii: Avoiding cross contamination of food. iv: Wash hands for 30 seconds when entering the food prepration area v: Wearing gloves when handling food. | Minor | i: Fridges and Freezers at venue use appropriately ii: food purchased on the day the camp begins iii: Wash all items touching food with hot soapy water beofre it touches another food item iv: Providing gloves for food preparers. v: Enforcing requirement to wash hands for people entering kitchen | i: EA ii: JA iii: EA iv: EA v: EA | i: 19/11 ii: 19/11 iii: ongoing iv: 19/11 v: ongoing | i: 1 ii: 5 iii: 2 iv: 4 v: 3
10 | Health and Safety | Electrocution or power failure | death, severe injury event, power trips | A: faulty cables/appliance B: Cables hanging incorrectly C: unqualified people working with electrics | Unlikely | Moderate | Minor | JS / JA / EA | i: We aren't taking an electraical equipment, we will use appliance already at venue | Low | i: Check with Manjedal manager that appliances are in working order ii:Follow manager instructions on proper usage of equipment | i: JS ii: JS | i: 19/11 ii: ongoing | i: 1 ii: 2
12 | Health and Safety | Volunteers/Staff not arriving | Short on first aiders Short on bar staff Unauthorised patron entry | A; Improper communication with staff confiming shifts B: sickness last minute cancellations | Likely | Minor | Minor | JS / JA / EA | i: Communications occur before event confiming staff ii: More volunteers than required to manage the alcohol sourced and first aid requirements iii: Staff briefing before event to re-allocate jobs if required | Low | i: Recruitment of volunteers from trusted officials of the club (Committee & Subgroups) ii: communication to volunteers and confimation of their receipt of the information iii: briefing just before event start | i: JS ii: EA iii: JS | i: 19/11 ii: 19/11 iii: 19/11 | i: 3 ii: 2 iii: 1
13 | Reputation | Litter | Untidy area risk of death or injury to Manjedal wildlife | A: Not enough bins B: Area not cleared of litter and rubbish post event | Possible | Minor | Minor | JS / JA / EA | i: Staff are designated to during event clean up ii: Sufficient Bins are present at venue iii: Continuous monitoring of rubbish levels and encouraging members to continually clean up | Low | i: Recruitment of volunteers and actions of staff during event for clean up ii: Whole committee to do post event litter and rubbish collection iii: check skip is present at venue | i: EA ii: EA iii: EA | i: ongoing ii: 19/11 iii: 19/11 | i: 3 ii: 2 iii: 1
14 | Reputation | Noise from the event causing disruption to non attendees | Negative attention Having to deal with the incident on the night | A: Excited discussions of patrons and loud music create loud nosies | Unlikely | Minor | Moderate | JS / JA / EA | i: Manjedal manager to have our contact info in case of issue ii: Music only to be played inside and until midnight | Minor | i: ensure music stays inside ii: ensure Manjedal manager has our contact info | i: EA ii: JS | i: ongoing ii: 19/11 | i: 1 ii: 2
15 | Legislative Requirements (Duty of Care) | Atendees being unable to arrive/leave event | Attendees do not organise their own transport to event, attendee's transport home becomes unavailable | A: Ineffective communication with attendees B: Attendee's carpool becomes unavailable C: Attendee needs to leave event early | Unlikely | Moderate | Minor | JS / JA / EA | i: Tickets and marketing state that attendees must make their own way to and from camp ii: A number of committee members will drive with space left in their vehicles should other club members require alternate transport iii: camp leaders will remain sober should an attendee need to be returned home early | Low | i: Efficient communication to attendees about transport to and from event ii: committee members have spare room in vehicles iii: camp leaders remain sober | i: JS ii: EA iii: JS | i: 19/11 ii: 19/11 iii: ongoing | i: 1 ii: 2 iii: 3
16 | Legislative Requirements (Duty of Care) | Patrons arriving with alcohol or illicit substances. Patrons consuming their own alcohol during the event | Death, Legal ramifications, Rapid intoxication | A: inefficient marketing B: Allowing guests to bring in backpacks C: allowing guest to bring in bottles | Possible | Moderate | Moderate | JS / JA / EA | i: Marketing - stating all BYO must be labelled and surrendered to camp leaders on arrival to event ii: Unsurrendered items to be confiscated by camp leaders | Minor | I; Make code of conduct clear ii: Effective staff briefing iii: Imposition on limits to the level and rate of alcohol consumption by patrons through RSA's limiting alcohol providence | i: JS ii: JS iii: JA | i: 19/11 ii: 19/11 iii: ongoing | i: 2 ii: 3 iii: 1
17 | Legislative Requirements (Duty of Care) | Patrons who are under the age of 18 at camp | Legal ramifications including fines, event closed. Duty of Care broken, negative attention from UWA | A: ID not checked upon ticket purchase | Unliekly | Major | High | JS / JA / EA | i: Marketing - event advertised as 18+ event, ID required ii: ID checked upon ticket purchase | Minor | i: Effective marketing ii: ID checked on ticket purchase | i: JS ii: JA | i: ongoing ii: ongoing | i: 2 ii: 1
18 | Health and Safety | Venue not available to storm/flooding | Attendees not made aware of event cancellation due to inclement weather | A: Ineffective communication with attendees | Unlikely | Moderate | Moderate | JS / JA / EA | i: Effectively communicate with attendees via all available channels ii: Call other camp leaders and committee members to ensure message has been recieved iii: Check weather forecast during week leading up to event | Minor | i: Effective communication with leaders and commitee ii: Check weather forecast during week leading up to event | i: JS ii: JA | i: ongoing ii: ongoing | i: 1 ii: 2
19 | Health and Safety | Sun exposure | Attendees get sun burnt, sunstroke, heatstroke | A: No sunscreen B: Attendees spent a long time in outside | Possible | Moderate | High | JS / JA / EA | i: Sunscreen will be avaiable at event ii: Attendees will be reminded to apply sunscreen and wear hats for outside event iii: Most events will be inside | Minor | i: Make sunscreen available ii: Remind attendees to apply sunscreen before outside event | i: JA ii: JA | i: 19/11 ii: 19/11 | i: 1 ii: 2

## Consequence Likelihood
Risk Definition and Classification
The following information is based upon AS/NZS 4360 Risk Management and information provided by the West Australian Insurance Commission.
Consequence
Level | Description | Financial Impact | Health | Reputation | Operations
1 | Insignificant | Less than $1000 | No injuries | Unsubstantiated, low impact, low profile or no news item | Little impact
2 | Minor | $1000 - $10,000 | First Aid Treatment | Substantiated, low impact, low news profile | Inconvenient delays
3 | Moderate | $10,000 - $50,000 | Medical treatment | Substantiated, public embarrassment, moderate impact, moderate news profile | Significant delays to major deliverables
4 | Major | $50,000 - $150,000 | Death or extensive injuries | Substantiated, public embarrassment, high impact news profile, third party actions | Non achievement of major deliverables
5 | Catastrophic | More than $150,000 | Multiple death or severe permanent disabilities | Substantiated, public embarrassment, very high multiple impacts, high widespread multiple news profile, third party actions | Non achievement of key objectives
Likelihood
Level | Description | Examples | Frequency
A | Almost certain | Expected to occur in most circumstances | More than once per year
B | Likely | Will probably occur in most circumstances | At least once per year
C | Possible | Should occur at some time | At least once in 3 years
D | Unlikely | Could occur at some time | At least once in 10 years
E | Rare | May occur, only in exceptional circumstances | Less than once in 15 years
Level of Risk
Likelihood | Insignificant 1 | Minor 2 | Moderate 3 | Major | Catastrophic 5
4
A- Almost Certain | High | High | Extreme | Extreme | Extreme
B- Likely | Moderate | High | High | Extreme | Extreme
C – Possible | Low | Moderate | High | Extreme | Extreme
D – Unlikely | Low | Low | Moderate | High | Extreme
E - Rare | Low | Low | Moderate | High | High

## drop down lists
Category of Risk | Generic Risk | Likelihood | Consequence | Matrix
| Reputation | Rare | Insignificant | Low
| Health and Safety | Unlikely | Minor | Minor
| Legislative Requirements (Duty of Care) | Possible | Moderate | Moderate
| Financial | Likely | Major | Major
|  | Probable | Catastrophic | Extreme
#